## Risk Analysis
Risk name | CAUSE description | CONSEQUENCE (event) description | EFFECT (outcome) description | Category | Probability (RFMEA Likelihood) | Impact | Detection | RPN | Risk Score | Risk Management Strategy | Preventive Action | Risk Response | Trigger | Risk Owner | Metrics | Frequency of data collection | Measurement method | Average effort expected from risk owner (in hours per time unit: day, week, month, year) | The scale used
Incompliance with Copyright (IP Protection) Law | Authors of individual articles either accidentally or deliberately infringe Copyright Law and violate third party's IP rights. | Third party sues Portal for infringement. | NGO managing portal has to pay huge fines to third party, goes bankrupt, cease to exist and portal has to be shut down. | Legal | 5 | 9 | 2 | 45 | 90 | Transfer | Include compliance framework in acceptable usage policy. Request written statements of all authors that their articles have no IP infringment included. Not publishing articles without signed statement attached. | Remove the content from the portal until further investigation is complete. Inform third party about corrective measures and next steps planned. | Third party complaint or personal conclusion of the risk owner. | Content Manager | Presence of the written statement from author that no IP rights were infringed attached to the document (binary variable - statement either is attached or is not attached) | Daily | Algorithmic (Comparison with predefined expected value) | 5 (week) | binary
Incompliance with Personal Data Protection Law | Personal data of registered users of the portal are not handled according to the PDPL and regular reports have not been sent to the Agency for Personal Data Protection (APDP) | Agency for Personal Data Protection sues NGO for not respecting (fulfilling) legal requests. | NGO managing portal has to pay huge fines to the Agency, goes bankrupt, cease to exist and portal has to be shut down. | Legal | 4 | 9 | 2 | 36 | 72 | Avoidance | Fulfill all the requirements of the PDPL on annual basis. Set up regular reporting schedule in the event calendar. | Send report or present previous reports and official correspondence with the Agency. | Official control request from the Agency. | Site Administrator | Reports submitted as requested by law (binary variable) | Annually | Algorithmic (Comparison with predefined expected value) | 8 (year) | binary
Incompliance with Anti-discrimination Law | Content contributors publish difamatory or otherwise abusive content on the portal. | Third party sues Portal for infringement. | NGO managing portal has to pay huge fines to third party, goes bankrupt, cease to exist and portal has to be shut down. | Legal | 6 | 9 | 5 | 54 | 270 | Avoidance | Include compliance framework in acceptable usage policy. | Remove the content from the portal until further investigation is complete. Inform third party about corrective measures and next steps planned. | Third party complaint or personal conclusion of the risk owner. | Community Manager | Number of difamatory, offending or otherwise unacceptable postings per week | Weekly | Subjective | 5 (week) | numeric
Incompliance with Electronic Media Law | NGO in charge of the portal has not fulfilled all the requirements of the Electronic Media Law related to portal registration, its legal and tax status. | Agency for Electronic Media sues NGO for not respecting (fulfilling) legal requests. | NGO managing portal has to pay huge fines to the Agency, goes bankrupt, cease to exist and portal has to be shut down. | Legal | 4 | 9 | 2 | 36 | 72 | Avoidance | Fulfill all the requirements of the law on annual basis. Set up regular reporting schedule in the event calendar. | Send report or present previous reports and official correspondence with the Agency. | Official control request from the Agency. | Portal Editor | Reports submitted as requested by law (binary variable) | Annually | Algorithmic (Comparison with predefined expected value) | 8 (year) | binary
Incompliance with Associations Law | NGO in charge of the portal has not fulfilled all the requirements of the Associations Law related to its registration and legal status. | NGO is officially declared non-existent (abolished, ceased to exist) by the authorities. | Portal has to be shut down. | Legal | 3 | 10 | 2 | 30 | 60 | Avoidance | Fulfill all the requirements of the law on regular basis. Request meetings with legal representative of the authorities when needed. | Take all necessary legal steps to get compliant as soon as possible. | Law changes. | Project Manager | All documents submitted as requested by law (binary variable) | Annually / When needed | Algorithmic (Comparison with predefined expected value) | 16 (year) | binary
Unclear sign-off authority on behalf of main sponsor | Sponsorship contract cannot be signed neither by the authorised subsidiary representative nor by regional manager in charge of funding CSR programs in CEE. | Unclear VAT treatment of the donation/sponsorship. | Potential fines from the Ministry of Finance (following annual financial reports) may force NGO to go bankrupt and shut down the portal. | Legal | 7 | 7 | 6 | 49 | 294 | Transfer | Clarify in advance authorities of different stakeholders representing sponsor(s) | Request clarification from sponsor. | Contract proposal returns unsigned. | Project Manager | Clear information/input present from the sponsor (binary variable) | When needed | Algorithmic (Comparison with predefined expected value) | 8 (year) | binary
Posts as a form of marketing, not publishing relevant information | Content contributors publish posts marketing their services instead of providing relevant information on the portal. | Negative reactions from other customers and users of the portal. | Reduced number of users and harmed image of the portal and responsible NGO. | Ethical | 9 | 4 | 6 | 36 | 216 | Mitigation | Clearly address issue in acceptable usage policy. Request formal signoff of acceptance of user rights during registration (access) to the portal. | Warn publisher and request modifications of the content. Removal of content from the portal. | Content submission received or content published in the communications area (Forum) of the portal. | Content Manager | Number of promotional/marketing articles handled in time unit | Weekly | Subjective | 4 (week) | numeric
Excessive amount and presence of advertisements from main sponsor | Too much sponsor advertisements. | Negative reactions from other sponsors and users of the portal. | Reduced number of users and harmed image of the portal and responsible NGO. | Ethical | 8 | 4 | 4 | 32 | 128 | Mitigation | Clearly address issue in acceptable usage policy. Specify maximal acceptable amount of advertisements on the portal in advance. | Warn publisher and request adjustment of the amount of advertisements. Removal of certain advertisements from the portal. | Number of advertisements reaches certain limit. Complaints from end-users. | Portal Editor | Number of advertisements published in time unit | Weekly | Algorithmic (Comparison with predefined expected value) | 2 (week) | binary
Communication issues within the project team | Different communication styles and expectations from project team members. | Frequent conflicts on project team meetings and through other communication channels. | Diminished trust, team cohesion and project morale. Departure of individual project team members from the project. | Ethical | 6 | 8 | 3 | 48 | 144 | Avoidance | Written signoff of the Team Charter by all project team members. Teambuilding activities and communication guidelines/trainings during project kick-off meeting. | Conflict resoultion in line with Team Charter. | Conflict noticed or reported. | Project Manager | Presence of conflict report/notification. | When needed | Subjective | 2 (week) | numeric
Unacceptable exclusivity requests from sponsor(s) and partners | Request from one sponsor (or few of them) to exclude other sponsors or portal partners. | Negative reactions from other sponsors and users of the portal. | Reduced number of users and harmed image of the portal and responsible NGO. | Ethical | 6 | 4 | 9 | 24 | 216 | Mitigation | Clarify and communicate in advance available and acceptable sponsorship packages to all potential sponsors. Sign-off sponsorship contracts with all sponsors. | Present again sponsorship packages. | Request received. | Portal Editor | Alignment with existing sponsorship packages (binary variable) | When needed | Algorithmic (Comparison with predefined expected value) | 1 (month) | binary

## RPN Analysis
Risk name | RPN
Incompliance with Anti-discrimination Law | 54
Unclear sign-off authority on behalf of main sponsor | 49
Communication issues within the project team | 48
Incompliance with Copyright (IP Protection) Law | 45
Incompliance with Personal Data Protection Law | 36
Posts as a form of marketing, not publishing relevant information | 36
Incompliance with Electronic Media Law | 36
Excessive amount and presence of advertisements from main sponsor | 32
Incompliance with Associations Law | 30
Unacceptable exclusivity requests from sponsor(s) and partners | 24

## Risk Score Analysis
Risk name | Risk Score
Unclear sign-off authority on behalf of main sponsor | 294
Incompliance with Anti-discrimination Law | 270
Posts as a form of marketing, not publishing relevant information | 216
Unacceptable exclusivity requests from sponsor(s) and partners | 216
Communication issues within the project team | 144
Excessive amount and presence of advertisements from main sponsor | 128
Incompliance with Copyright (IP Protection) Law | 90
Incompliance with Personal Data Protection Law | 72
Incompliance with Electronic Media Law | 72
Incompliance with Associations Law | 60

## Scatter Plot Analysis
RPN | Risk Score | Risk name
45 | 90 | Incompliance with Copyright (IP Protection) Law
36 | 72 | Incompliance with Personal Data Protection Law
54 | 270 | Incompliance with Anti-discrimination Law
36 | 72 | Incompliance with Electronic Media Law
30 | 60 | Incompliance with Associations Law
49 | 294 | Unclear sign-off authority on behalf of main sponsor
36 | 216 | Posts as a form of marketing, not publishing relevant information
32 | 128 | Excessive amount and presence of advertisements from main sponsor
48 | 144 | Communication issues within the project team
24 | 216 | Unacceptable exclusivity requests from sponsor(s) and partners
Legend:
| RED | Critical Risks - those to focus on
| Yellow | Either high RPN or Risk Score
| Green | Low RPN and Risk Score

## Categorisation
Category | Risk name
Ethical | Communication issues within the project team
Ethical | Posts as a form of marketing, not publishing relevant information
Ethical | Excessive amount and presence of advertisements from main sponsor
Ethical | Unacceptable exclusivity requests from sponsor(s) and partners
Legal | Incompliance with Anti-discrimination Law
Legal | Incompliance with Associations Law
Legal | Incompliance with Copyright (IP Protection) Law
Legal | Incompliance with Electronic Media Law
Legal | Incompliance with Personal Data Protection Law
Legal | Unclear sign-off authority on behalf of main sponsor